## Timeline A
Date | Activity 1 | Activity 2 | Activity 3
2012-09-30 | Launch | Hibernate
2012-10-01 | Cruise to Moon
2012-10-02 | Cruise to Moon
2012-10-03 | Cruise to Moon
2012-10-04 | Cruise to Moon
2012-10-05 | Cruise to Moon
2012-10-06 | Arrive at Moon | Wake Up
2012-10-07 | System Check
2012-10-08 | Decent | Launch Penatrators | Landing
2012-10-09 | System Check | Drop of single site box
2012-10-10 | Rove to Rim of Schackelton Crator
2012-10-11 | Collect Data from Penetrators - all 15
2012-10-12 | Relay Data from Penetrators - all 15
2012-10-13 | System check
2012-10-14 | Sunday's Off
2012-10-15 | Rove to Lighted Site 1
2012-10-16 | Collect Data from Lighted Site 1
2012-10-17 | Relay Data from Lighted Site 1
2012-10-18 | Rove to Lighted Site 2
2012-10-19 | Collect Data from Lighted Site 2
2012-10-20 | System check
2012-10-21 | Sunday's Off
2012-10-22 | Relay Data from Lighted Site 2
2012-10-23 | Rove to Lighted Site 3
2012-10-24 | Collect Data from Lighted Site 3
2012-10-25 | Relay Data from Lighted Site 3
2012-10-26 | Rove to Lighted Site 4
2012-10-27 | System check
2012-10-28 | Sunday's Off
2012-10-29 | Collect Data from Lighted Site 4
2012-10-30 | Relay Data from Lighted Site 4
2012-10-31 | Rove to Lighted Site 5
2012-11-01 | Collect Data from Lighted Site 5
2012-11-02 | Relay Data from Lighted Site 5
2012-11-03 | System check
2012-11-04 | Sunday's Off
2012-11-05 | Rove to Lighted Site 6
2012-11-06 | Collect Data from Lighted Site 6
2012-11-07 | Relay Data from Lighted Site 6
2012-11-08 | Rove to Lighted Site 7
2012-11-09 | Collect Data from Lighted Site 7
2012-11-10 | System check
2012-11-11 | Sunday's Off
2012-11-12 | Relay Data from Lighted Site 7
2012-11-13 | Rove to Lighted Site 8
2012-11-14 | Collect Data from Lighted Site 8
2012-11-15 | Relay Data from Lighted Site 8
2012-11-16 | Rove to Lighted Site 9
2012-11-17 | System check
2012-11-18 | Sunday's Off
2012-11-19 | Collect Data from Lighted Site 9
2012-11-20 | Relay Data from Lighted Site 9
2012-11-21 | Thanksgiving Break
2012-11-22
2012-11-23
2012-11-24 | System check
2012-11-25 | Sunday's Off
2012-11-26 | Rove to Lighted Site 10
2012-11-27 | Collect Data from Lighted Site 10
2012-11-28 | Relay Data from Lighted Site 10
2012-11-29 | Rove to Lighted Site 11
2012-11-30 | Collect Data from Lighted Site 11
2012-12-01 | System check
2012-12-02 | Sunday's Off
2012-12-03 | Relay Data from Lighted Site 11
2012-12-04 | Rove to Lighted Site 12
2012-12-05 | Collect Data from Lighted Site 12
2012-12-06 | Relay Data from Lighted Site 12
2012-12-07 | Rove to Lighted Site 13
2012-12-08 | System check
2012-12-09 | Sunday's Off
2012-12-10 | Collect Data from Lighted Site 13
2012-12-11 | Relay Data from Lighted Site 13
2012-12-12 | Rove to Lighted Site 14
2012-12-13 | Collect Data from Lighted Site 14
2012-12-14 | Relay Data from Lighted Site 14
2012-12-15 | System check
2012-12-16 | Sunday's Off
2012-12-17 | Rove to Lighted Site 15
2012-12-18 | Collect Data from Lighted Site 15
2012-12-19 | Relay Data from Lighted Site 15
2012-12-20 | Rove to Lighted Site 16
2012-12-21 | Collect Data from Lighted Site 16
2012-12-22 | System check
2012-12-23 | Christmas Break
2012-12-24
2012-12-25
2012-12-26
2012-12-27
2012-12-28 | Relay Data from Lighted Site 16
2012-12-29 | System check
2012-12-30 | Sunday's Off
2012-12-31 | New Year's Break
2013-01-01
2013-01-02
2013-01-03 | Rove to Lighted Site 17
2013-01-04 | Collect Data from Lighted Site 17
2013-01-05 | System check
2013-01-06 | Sunday's Off
2013-01-07 | Relay Data from Lighted Site 17
2013-01-08 | Rove to Lighted Site 18
2013-01-09 | Collect Data from Lighted Site 18
2013-01-10 | Relay Data from Lighted Site 18
2013-01-11 | Rove to Lighted Site 19
2013-01-12 | System check
2013-01-13 | Sunday's Off
2013-01-14 | Collect Data from Lighted Site 19
2013-01-15 | Relay Data from Lighted Site 19
2013-01-16 | Rove to Lighted Site 20
2013-01-17 | Collect Data from Lighted Site 20
2013-01-18 | Relay Data from Lighted Site 20
2013-01-19 | System check
2013-01-20 | Sunday's Off
2013-01-21 | Martin Luther King's Birthday
2013-01-22 | Rove to Lighted Site 20
2013-01-23 | Collect Data from Lighted Site 20
2013-01-24 | Relay Data from Lighted Site 20
2013-01-25 | Rove to Lighted Site 21
2013-01-26 | System check
2013-01-27 | Sunday's Off
2013-01-28 | Collect Data from Lighted Site 21
2013-01-29 | Relay Data from Lighted Site 21
2013-01-30 | Rove to Lighted Site 22
2013-01-31 | Collect Data from Lighted Site 22
2013-02-01 | Relay Data from Lighted Site 22
2013-02-02 | System check
2013-02-03 | Sunday's Off
2013-02-04 | Rove to Lighted Site 23
2013-02-05 | Collect Data from Lighted Site 23
2013-02-06 | Relay Data from Lighted Site 23
2013-02-07 | Rove to Lighted Site 24
2013-02-08 | Collect Data from Lighted Site 24
2013-02-09 | System check
2013-02-10 | Sunday's Off
2013-02-11 | Relay Data from Lighted Site 24
2013-02-12 | Rove to Lighted Site 25
2013-02-13 | Collect Data from Lighted Site 25
2013-02-14 | Relay Data from Lighted Site 25
2013-02-15 | Rove to Lighted Site 26 |  |  | Rove to Lighted Site 30
2013-02-16 | System check |  |  | Collect Data from Lighted Site 30
2013-02-17 | Sunday's Off |  |  | Relay Data from Lighted Site 30
2013-02-18 | President's Day Off
2013-02-19 | Collect Data from Lighted Site 26
2013-02-20 | Relay Data from Lighted Site 26
2013-02-21 | Rove to Lighted Site 27
2013-02-22 | Collect Data from Lighted Site 27
2013-02-23 | System check
2013-02-24 | Sunday's Off
2013-02-25 | Relay Data from Lighted Site 27
2013-02-26 | Rove to Lighted Site 28
2013-02-27 | Collect Data from Lighted Site 28
2013-02-28 | Relay Data from Lighted Site 28 |  |  | Rove to Lighted Site 28
2013-03-01 | Rove to Lighted Site 29 |  |  | Collect Data from Lighted Site 28
2013-03-02 | System check |  |  | Relay Data from Lighted Site 28
2013-03-03 | Sunday's Off |  |  | Rove to Lighted Site 29
2013-03-04 | Collect Data from Lighted Site 29 |  |  | Collect Data from Lighted Site 29
2013-03-05 | Relay Data from Lighted Site 29 |  |  | Relay Data from Lighted Site 29
2013-03-06 | Rove to site to Collect Sample for SRV
2013-03-07 | Collect Sample for SRV
2013-03-08 | Launch SRV
2013-03-09 | System check
2013-03-10 | Sunday's Off
2013-03-11 | Rove to Lighted Site 30
2013-03-12 | Collect Data from Lighted Site 30
2013-03-13 | Relay Data from Lighted Site 30
2013-03-14 | Rove to Lighted Site 31
2013-03-15 | Collect Data from Lighted Site 31
2013-03-16 | System check
2013-03-17 | Sunday's Off
2013-03-18 | Relay Data from Lighted Site 31
2013-03-19 | Rove to Lighted Site 32
2013-03-20 | Collect Data from Lighted Site 32
2013-03-21 | Relay Data from Lighted Site 32
2013-03-22 | Rove to Lighted Site 33
2013-03-23 | System check
2013-03-24 | Sunday's Off
2013-03-25 | Collect Data from Lighted Site 33
2013-03-26 | Relay Data from Lighted Site 33
2013-03-27 | Rove to Lighted Site 34
2013-03-28 | Collect Data from Lighted Site 34
2013-03-29 | Good Friday Off
2013-03-30 | System Check
2013-03-31 | Easter Sunday's Off
2013-04-01 | Easter Vacation Off
2013-04-02 | Relay Data from Lighted Site 34
2013-04-03 | Rove to Lighted Site 35
2013-04-04 | Collect Data from Lighted Site 35
2013-04-05 | Relay Data from Lighted Site 35
2013-04-06 | System check
2013-04-07 | Sunday's Off
2013-04-08 | Rove to Lighted Site 36
2013-04-09 | Collect Data from Lighted Site 36
2013-04-10 | Relay Data from Lighted Site 36
2013-04-11 | Rove to Lighted Site 37
2013-04-12 | Collect Data from Lighted Site 37
2013-04-13 | System check
2013-04-14 | Sunday's Off
2013-04-15 | Relay Data from Lighted Site 37
2013-04-16 | Rove to Lighted Site 38
2013-04-17 | Collect Data from Lighted Site 38
2013-04-18 | Relay Data from Lighted Site 38
2013-04-19 | Rove to Lighted Site 39
2013-04-20 | System check
2013-04-21 | Sunday's Off
2013-04-22 | Collect Data from Lighted Site 39
2013-04-23 | Relay Data from Lighted Site 39
2013-04-24 | Rove to Lighted Site 40
2013-04-25 | Collect Data from Lighted Site 40
2013-04-26 | Relay Data from Lighted Site 40
2013-04-27 | System check
2013-04-28 | Sunday's Off
2013-04-29 | Rove to Lighted Site 40
2013-04-30 | Collect Data from Lighted Site 40
2013-05-01 | Relay Data from Lighted Site 40
2013-05-02 | Rove to Lighted Site 41
2013-05-03 | Collect Data from Lighted Site 41
2013-05-04 | System check
2013-05-05 | Sunday's Off
2013-05-06 | Relay Data from Lighted Site 41
2013-05-07 | Rove to Lighted Site 42
2013-05-08 | Collect Data from Lighted Site 42
2013-05-09 | Relay Data from Lighted Site 42
2013-05-10 | Rove to Lighted Site 43
2013-05-11 | System check
2013-05-12 | Sunday's Off
2013-05-13 | Collect Data from Lighted Site 43
2013-05-14 | Relay Data from Lighted Site 43
2013-05-15 | Rove to Lighted Site 44
2013-05-16 | Collect Data from Lighted Site 44
2013-05-17 | Relay Data from Lighted Site 44
2013-05-18 | System check
2013-05-19 | Sunday's Off
2013-05-20 | Rove to Lighted Site 45
2013-05-21 | Collect Data from Lighted Site 45
2013-05-22 | Relay Data from Lighted Site 45
2013-05-23 | Rove to Lighted Site 46
2013-05-24 | Collect Data from Lighted Site 46
2013-05-25 | System check
2013-05-26 | Sunday's Off
2013-05-27 | Memorial Day
2013-05-28 | Relay Data from Lighted Site 46
2013-05-29 | Rove to Lighted Site 47
2013-05-30 | Collect Data from Lighted Site 47
2013-05-31 | Relay Data from Lighted Site 47
2013-06-01 | System check
2013-06-02 | Sunday's Off
2013-06-03 | Rove to Lighted Site 48
2013-06-04 | Collect Data from Lighted Site 48
2013-06-05 | Relay Data from Lighted Site 48
2013-06-06 | Rove to Lighted Site 49
2013-06-07 | Collect Data from Lighted Site 49
2013-06-08 | System check
2013-06-09 | Sunday's Off
2013-06-10 | Relay Data from Lighted Site 49
2013-06-11 | Rove to Lighted Site 50
2013-06-12 | Collect Data from Lighted Site 50
2013-06-13 | Relay Data from Lighted Site 50
2013-06-14 | Rove to Lighted Site 51
2013-06-15 | System check
2013-06-16 | Sunday's Off
2013-06-17 | Collect Data from Lighted Site 51
2013-06-18 | Relay Data from Lighted Site 51
2013-06-19 | Rove to Lighted Site 52
2013-06-20 | Collect Data from Lighted Site 52
2013-06-21 | Relay Data from Lighted Site 52
2013-06-22 | System check
2013-06-23 | Sunday's Off
2013-06-24 | Rove to Lighted Site 53
2013-06-25 | Collect Data from Lighted Site 53
2013-06-26 | Relay Data from Lighted Site 53
2013-06-27 | Rove to Lighted Site 54
2013-06-28 | Collect Data from Lighted Site 54
2013-06-29 | System check
2013-06-30 | Sunday's Off
2013-07-01 | Relay Data from Lighted Site 54
2013-07-02 | Rove to Lighted Site 55
2013-07-03 | Collect Data from Lighted Site 55
2013-07-04 | July 4th Holiday
2013-07-05 | Relay Data from Lighted Site 55
2013-07-06 | System check
2013-07-07 | Sunday's Off
2013-07-08 | Rove to Lighted Site 56
2013-07-09 | Collect Data from Lighted Site 56
2013-07-10 | Relay Data from Lighted Site 56
2013-07-11 | Rove to Lighted Site 57
2013-07-12 | Collect Data from Lighted Site 57
2013-07-13 | System check
2013-07-14 | Sunday's Off
2013-07-15 | Relay Data from Lighted Site 57
2013-07-16 | Rove to Lighted Site 58
2013-07-17 | Collect Data from Lighted Site 58
2013-07-18 | Relay Data from Lighted Site 58
2013-07-19 | Rove to Lighted Site 59
2013-07-20 | System check
2013-07-21 | Sunday's Off
2013-07-22 | Collect Data from Lighted Site 59
2013-07-23 | Relay Data from Lighted Site 59
2013-07-24 | Rove to Rim of Schackelton Crator
2013-07-25 | Rove to Rim of Schackelton Crator
2013-07-26 | Alternate Rove to Penatrator Site 1
2013-07-27 | System check
2013-07-28 | Sunday's Off
2013-07-29 | Alternate Collect Data from Penatrator Site 1
2013-07-30 | Alternate Relay Data from Penatrator Site 1
2013-07-31 | Alternate Rove to Penatrator Site 2
2013-08-01 | Alternate Collect Data from Penatrator Site 2
2013-08-02 | Alternate Relay Data from Penatrator Site 2
2013-08-03 | System check
2013-08-04 | Sunday's Off
2013-08-05 | Alternate Rove to Penatrator Site 3
2013-08-06 | Alternate Collect Data from Penatrator Site 3
2013-08-07 | Alternate Relay Data from Penatrator Site 3
2013-08-08 | Alternate Rove to Penatrator Site 4
2013-08-09 | Alternate Collect Data from Penatrator Site 4
2013-08-10 | System check
2013-08-11 | Sunday's Off
2013-08-12 | Alternate Relay Data from Penatrator Site 4
2013-08-13 | Alternate Rove to Penatrator Site 5
2013-08-14 | Alternate Collect Data from Penatrator Site 5
2013-08-15 | Alternate Relay Data from Penatrator Site 5
2013-08-16 | Alternate Rove to Penatrator Site 6
2013-08-17 | System check
2013-08-18 | Sunday's Off
2013-08-19 | Alternate Collect Data from Penatrator Site 6
2013-08-20 | Alternate Relay Data from Penatrator Site 6
2013-08-21 | Alternate Rove to Penatrator Site 7
2013-08-22 | Alternate Collect Data from Penatrator Site 7
2013-08-23 | Alternate Relay Data from Penatrator Site 7
2013-08-24 | System check
2013-08-25 | Sunday's Off
2013-08-26 | Alternate Rove to Penatrator Site 8
2013-08-27 | Alternate Collect Data from Penatrator Site 8
2013-08-28 | Alternate Relay Data from Penatrator Site 8
2013-08-29 | Alternate Rove to Penatrator Site 9
2013-08-30 | Alternate Collect Data from Penatrator Site 9
2013-08-31 | System check
2013-09-01 | Sunday's Off
2013-09-02 | Labor Day Off
2013-09-03 | Alternate Relay Data from Penatrator Site 9
2013-09-04 | Alternate Rove to Penatrator Site 10
2013-09-05 | Alternate Collect Data from Penatrator Site 10
2013-09-06 | Alternate Relay Data from Penatrator Site 10
2013-09-07 | System check
2013-09-08 | Sunday's Off
2013-09-09 | Alternate Rove to Penatrator Site 11
2013-09-10 | Alternate Collect Data from Penatrator Site 11
2013-09-11 | Alternate Relay Data from Penatrator Site 11
2013-09-12 | Alternate Rove to Penatrator Site 12
2013-09-13 | Alternate Collect Data from Penatrator Site 12
2013-09-14 | System check
2013-09-15 | Sunday's Off
2013-09-16 | Alternate Relay Data from Penatrator Site 12
2013-09-17 | Alternate Rove to Penatrator Site 13
2013-09-18 | Alternate Collect Data from Penatrator Site 13
2013-09-19 | Alternate Relay Data from Penatrator Site 13
2013-09-20 | Alternate Rove to Penatrator Site 14
2013-09-21 | System check
2013-09-22 | Sunday's Off
2013-09-23 | Alternate Collect Data from Penatrator Site 14
2013-09-24 | Alternate Relay Data from Penatrator Site 14
2013-09-25 | Alternate Rove to Penatrator Site 15
2013-09-26 | Alternate Collect Data from Penatrator Site 15
2013-09-27 | Alternate Relay Data from Penatrator Site 15
2013-09-28 | System check
2013-09-29 | Sunday's Off
2013-09-30 | Power Down

## Mission Control
Position | Work Description | Work Type
Flight Director | Oversees entire mission | 2 Shifts
Rover Operator | Operates Camera to see where the rover is going and drive the rover on the surface of the moon | 2 Shifts
Data Analyst | Analyses the data sent back to Mission Control | 2 Shifts
Data Archivist | Archives the data collected | 2 Shifts
Scientist | Controls Experiments and data collection | 2 shifts
Communication Specialist | Controls the communications with the rover | 2 Shifts
Troubleshooter 1 | Troubleshoots any problems that arise | 2 Shifts
Troubleshooter 2 | Troubleshoots any problems that arise | 2 Shifts
Mission Planner | Plans the next day's missions | 2 Shifts

## Gantt Chart
| Start Date | Completed | Remaining
Baseline Review | 2008-01-22 | 10 | 0
Resume | 2008-02-01 | 21 | 0
Alternative Concept 1 Design | 2008-02-01 | 25 | 0
Alternative Concept 2 Design | 2008-02-01 | 25 | 0
Phase 2 First Draft | 2008-02-01 | 19 | 0
Phase 2 Second Draft | 2008-02-19 | 2 | 0
Phase 2 Final Draft | 2008-02-21 | 6 | 0
Phase 2 Presentation | 2008-02-19 | 8 | 0
Selection of Final Concept | 2008-02-21 | 11 | 0
Open House Poster | 2008-02-27 | 7 | 0
Phase 3 First Draft | 2008-02-26 | 29 | 0
Phase 3 Second Draft | 2008-03-26 | 17 | 0 | 17
Phase 3 Final Draft | 2008-04-11 | 0 | 19 | 20
Phase 3 Presentation | 2008-04-11 | 0 | 19
Final Design of Subsystems | 2008-02-26 | 45 | 15 | 65

## Risk Chart
| Likelihood | Consequences | Line Item | [6 empty] | # | Mission Criticality Level | Risk
1 | 5 | 3 | [7 empty] | 1 | high | Penatrator Failure - Penatrators fail upon impact or do not launch at all
2 | 4 | 3 | [7 empty] | 2 | medium | RTG Ovherheat - RTG puts out too much heat for the system to handle
3 | 4 | 4 | [7 empty] | 3 | high | Thermal Shutdown - the system gets overheats and shuts down
4 | 3 | 4 | [7 empty] | 4 | medium | Mobility - the drive system of the lander fails
5 | 3 | 3 | [7 empty] | 5 | medium | Camera Failure - the camera breaks and does not transmit images
6 | 2 | 4 | [7 empty] | 6 | medium | Structure Failure - the structure collapes
7 | 2 | 4 | [7 empty] | 7 | medium | Navigation - the navigation system fails
8 | 3 | 1 | [7 empty] | 8 | low | SRV Failure - the SRV fails to launch
9 | 4 | 1 | [7 empty] | 9 | low | Single Site Box - the box fails during the year
10 | 2 | 5 | [7 empty] | 10 | medium | Communications - loss of all communications with the rover
|  |  |  | 5 |  |  | 1
|  |  |  | 4 | 9 |  | 2 | 3
|  |  |  | 3 | 8 |  | 5 | 4
|  |  |  | 2 |  |  |  | 6,7 | 10
1
[5 empty] | 1 | 2 | 3 | 4 | 5 |  |  |  | Likelihood
[13 empty] | 1 | improbable
2
[13 empty] | 3 | probable
4
[13 empty] | 5 | definite
Consequences
[13 empty] | 1 | the mission can still be completed
2
[13 empty] | 3 | mission operates at limited capacity
4
[13 empty] | 5 | total mission failure
L
I
K
E
L
I
H
O
O
D
CONSEQUENCES